## Sheet1
Date | Day | Time | Work
2025-03-02 | Monday | 9:30am to 6:30pm | Excel on all user roles for KT and updated the links. Bugs in restated api, gri report download .
2025-04-02 | Tuesday | 9:30am to 6:30pm | Made mobile number non-mandatory in creating user. Emission factor value to right. Peer pdf UI things required by client. Breadcrumb bugs
2025-05-02 | Wednesday | 9:30am to 6:30pm | Screen level description for Peer Benchmarking and Targets modules. Stationary active tab bugs. Total and decimals updated acc to requirement.
2025-06-02 | Thursday | 9:30am to 6:30pm | GRI text alphabetical order, and save as draft and submit error fixed. Other UI text changes
2025-07-02 | Friday | 9:30am to 6:30pm | Created Edit company page with breadcrumb functionality. Adjusted margins in pdf. Modified financial year in peerpdf. Removed borad from board composition.
2025-10-02 | Monday | 9:30am to 6:30pm | Added margin to pdf footer top so that the table won't cut. New requirements from pdfs and excels. Added Edit api for changing Admin
2025-11-02 | Tuesday | 9:30am to 6:30pm | Peer pdf, Gri pdf and peer excel. Edit admin bugs . Displaying the total effluents discharged correctly in water module.
2025-12-02 | Wednesday | 9:30am to 6:30pm | Added prefilled api to effluents
13/2/2025 | Thursday | 9:30am to 6:30pm | Updated filters to audit view Prompt changes.
15/2/2025 | Friday | 9:30am to 6:30pm | PDF's - peer, custom, governance, safety, issb, water, waste, effluents, employee, board.
17/2/2025 | Monday | 9:30am to 6:30pm | PDF's - maturity and gri, UI bugs from client call
18/2/2025 | Tuesday | 9:30am to 6:30pm | Feedback points
19/2/2025 | Wednesday | 9:30am to 6:30pm | Bugs and rechecked the feedback points
20/2/2025 | Thursday | 9:30am to 6:30pm | Feedback from client call
21/2/2025 | Friday | 9:30am to 6:30pm | Bugs from UAT and sandbox
24/2/2025 | Monday | 9:30am to 6:30pm | ESG Handbook excel
25/2/2025 | Tuesday | 9:30am to 6:30pm | Clients points from 24 and 25feb, handbook remodified
26/2/2025 | Wednesday | 9:30am to 6:30pm | No data pdfs
27/2/2025 | Thursday | 9:30am to 6:30pm | Client Uat bug sheet
28/2/2025 | Friday | 9:30am to 6:30pm | Updated logo in sustain ai new demo dev and removed kpmg things